## Cover
TEST PLAN
Project Name | FPT SHOP |  |  | Reviewer | TranMinhTuong
Project Code | FPT SHOP |  |  | Review date | 2024-11-01
Creator | TranMinhTuong |  |  | Approver | HienBTT
Version | v1.0 |  |  | Approval Date | 2024-11-01
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
2024-11-01 | v1.0 | Initial | A
Index
Sheet Name | Description |  |  |  | Note
Cover | Title page
Test Policy | - General policy for Test process, Test case design, Test Data - List of requirements to Test/not Test - Exit criteria for testing - Suspension criteria and Resumption requirements
Test Management | - Test scope - Deliverable - Management method - Risk - Assumption - Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Appendix | - Description and detailed definition of Test level, types and techniques - List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
21130604_TestDesign |  |  |  | 0.5
Note on E10: ====== ID#AAAAHNbKGmo (2020-11-08 05:44:12) - A: Added - D: Deleted - M: Modified

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
| # | Description | Responsibility | Note
| 1 | Ensure that all product-related information, such as images, names, colors, and customer details, are displayed accurately and fully across the system. | TranMinhTuong | Conduct periodic testing and promptly report any defects to ensure minimal disruption to project timelines.
| 2 | Perform testing for core functionalities, including product display, customer information entry, and order confirmation.
Test case design policy
Description of policies of test case design.
| # | Items | Note
| 1 | Each test case should contain clear step-by-step execution instructions along with expected results to ensure consistency in test execution. | Update test cases whenever there is a change in functional requirements to keep them aligned with the latest project needs.
| 2 | Test cases must cover all critical functionalities, especially edge cases and scenarios likely to trigger exceptional system behaviors.
Quality metric
Description of target
| # | Items | Target | Note
|  | Test Coverage: Ensure that at least 90% of all critical functionalities are covered by test cases to verify that all key areas of the application are tested thoroughly. | ≥ 90% | This includes both functional and non-functional requirements to ensure a comprehensive assessment of the software quality.
|  | Test Execution Efficiency: Achieve a minimum test execution rate of 95% for all planned test cases within the scheduled timeframe to ensure timely testing completion. | ≥ 95% | Prioritize high-risk areas for early testing and maintain execution logs to track progress effectively.
|  | Defect Leakage: Limit defect leakage (defects found after release) to less than 5% to ensure that most issues are identified and resolved during the testing phase. | < 5% | Focus on thorough regression and acceptance testing to minimize defect leakage.
|  | Defect Density: Maintain a defect density of less than 1 defect per 1,000 lines of code for critical modules to ensure minimal disruptions in core functionalities. | < 1 defect per 1,000 LOC (Lines of Code) | High priority should be given to modules with high defect density for further quality improvement.
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
| # | Criteria | Priority | Note
| 1 | 80% of completed test cases / total test cases (test coverage > 80%) | High | Begin with high-priority test cases that cover critical functionalities. Once these are validated, proceed to medium- and low-priority cases.
| 2 | Test successful coverage >= 80% | Medium | Focus on validating major user flows and use cases first to ensure essential features work correctly before moving to edge cases.
| 3 | Software is correct with SRS | Critical | Conduct final validation checks against the SRS document to ensure no critical requirements are missed. This step is essential before approving software for release.
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
| # | Suspension Criteria | Note
| 1 | When a defect is introduced that cannot allow any further testing | Major defects blocking core functionalities should be documented and reported to the development team immediately for a prioritized fix.
| 2 | A specific holiday shuts down both development and testing (Tet Holiday) | Ensure all ongoing work is saved and documented before the holiday period to facilitate a smooth resumption post-holiday.
| 3 | If there is any network, hardware problem in the organisation, we can suspend testing | Contact IT support for prompt troubleshooting and document any delays caused by technical issues.
| 4 | If we got more pending requests with the development team | Communicate with the development team to prioritize and address these requests. Testing should resume once critical pending items are resolved.
| 5 | Frequent Test Environment Instability: If the test environment is repeatedly unstable or has configuration issues, pause testing until stability is restored. | Notify the project manager to address resource allocation issues before resuming testing.
| 6 | Insufficient Testing Resources: Testing should be suspended if there is a lack of essential resources, such as testing environments, tools, or personnel. | Coordinate with the IT team to identify and resolve recurring environment problems.
| # | Resumption Requirements | Note
| 1 | When the particular issue has been addressed and solved | Perform a quick retest on affected areas to confirm stability before proceeding with the remaining test cases

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Create test plan | Outline the scope, objectives, and approach for the testing process. |  | Leader / Testers
2 | Create test design | Design test cases and scenarios based on requirements. |  | Tester
3 | Create test cases | Develop detailed test cases to validate functionalities. |  | Tester
4 | Create test data | Generate necessary data inputs for testing scenarios. |  | Teseter
5 | Execute system test | Perform system-level testing to validate integration and functionality. |  | Teseter
6 | Defects list | Document defects found during testing for resolution tracking. |  | Teseter
7 | Create test report | Summarize testing results and provide a final evaluation. |  | Leader / Testers
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 2024-11-01 | Test leader | Test manager, Team | This document itself
2 | Test cases | 2024-11-02 | Test leader | Test manager, Team
3 | Defect logs | 2024-11-05 | Test leader | Test manager, Team
4 | Test report | 2024-11-10 | Test leader | Test manager, Team
Management method
Describe the management method of test process.
# | Object | Method |  |  | Note
1 | Test Case Management | Use a test management tool (e.g., JIRA) to organize and track test cases |  |  | Regularly update test case status
2 | Defect Tracking | Employ a defect tracking system to log and monitor issues |  |  | Prioritize defects based on severity; check defect status daily
3 | Test Environment Management | Set up and maintain stable test environments for all test phases |  |  | Conduct environment checks weekly; last validation date
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  | Mitigation |  | Contingency
1 | Team members lack experience in software testing domain |  | Plan training course to skill up your members |  | 1. Connect with a training organization 2. Attend mandatory training 3. Quality test
2 | The development team improved the code which led to the testing process being paused |  | Accept this risk |  | Contact the development team
3 | The project schedule is too tight; it's hard to complete this project on time |  | Set test priority for each test case and execute the test case with the highest priority |  | 1. Determine the priority for each test case 2. Set priority for each test case 3. Follow the priority level
4 | Members misunderstood the request |  | Organize to review and analyze requirements to member before starting the testing process |  | 1. Hold a meeting 2. Review required 3. Inspections
5 | Employees reduce working performance after Tet holiday |  | Accept this risk |  | OT to keep up with the schedule
6 | Limited Resource Availability: In case of a resource shortage, prioritize high-impact test cases. |  | Reassign resources or reschedule testing activities as needed |  | Coordinate with project management for temporary resource allocation.
7 | High Defect Count in Initial Testing Phase: If numerous defects are found early, it may delay testing timelines |  | Address critical defects first; communicate impacts to the team |  | Allocate additional testing time or resources if necessary.
Assumption
Listing of all assumption of test process.
# | Type | Description
1 | Availability of Test Environment | Assume the test environment will be fully set up and stable by the scheduled start date.
2 | Requirements Stability | Assume that requirements will not change significantly once testing begins.
Training Plan
Plan training for test team.
# | Training Topic | Description |  | Responsibility | Start Date | End Date
1 | Introduction to Testing Tools | Basic usage and features of testing tools used in the project. |  | Leader | 2024-11-01 | 2024-11-03
2 | Test Case Design and Documentation | Focus on best practices for designing comprehensive test cases. |  | Tester | 2024-11-04 | 2024-11-06
3 | Defect Tracking and Management | Emphasize methods to report and manage defects efficiently. |  | QA | 2024-11-07 | 2024-11-09
Note on E32: ====== ID#AAAAHNbKGmc (2020-11-08 05:44:12) steps keep a risk from occurring or driving its impact to an acceptance level
Note on G32: ====== ID#AAAAHNbKGmk (2020-11-08 05:44:12) steps would have to be done if the risk were to become reality
Note on B43: ====== ID#AAAAHNbKGmY It can be (2020-11-08 05:44:12) - Requirement - Test Products - Test environment - Test tools ...

## Test Strategy
Test Strategy
Test Objective:
Ensure the software is free from major bugs before release and that it meets all defined requirements, providing a reliable and user-friendly experience for customers.
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing | Regression Testing | Performance Testing
Test techniques
White box testing | x |  | x |  | x
Load testing | [5 empty] | x
stress testing | [5 empty] | x
Black box testing |  | x | x | x
Responsibility | Developer | Tester | Tester | Tester | Tester | Tester
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
All Functions of the ProlTM system described in screen design document, the functions are tested in order of priority from high to low (highest priority tested first) |  | 21130604_TestDesign |  |  | Test coverage prioritizes critical functions to ensure main functionalities are fully verified before release.
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop, Tablet, Smartphone |  |  |  | Standard Fsoft configuration used for testing
OS | Window 10 64bit Mac10.14.5 Android 6.0 or higher
Software | Chrome version 78.0.3904.97 Firefox 70.0 Edge 44.18362.329.0
Database | MS SQL
Browser | IE/FireFox, Chrome
Network configured | LAN Wifi
Note on G10: ====== ID#AAAAHNbKGmg (2020-11-08 05:44:12) - manual - test tool …

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
1 | TranMinhTuong | Tester | Read and analyze documents, create test design, create test cases, execute test cases, log bugs, evaluate exit criteria, and compile the test report.
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan | 2024-11-01 | 2024-11-02
2 | Create test design | 2024-11-01 | 2024-12-20
3 | Create test case | 2024-11-01 | 2024-11-04
4 | Execute test and log bugs | 2024-11-01 | 2024-12-21
5 | Evaluting exit criteria & Test report | 2024-11-01 | 2024-12-21
6 | Review | 2024-11-01 | 2024-12-21
| Task | Start day from 1/11/2024 | Duration
| Create test plan | 0 | 1
| Create test design | -1 | 49
| Create test case | -2 | 3
| Execute test and log bugs | -3 | 50
| Evaluting exit criteria & Test report | -4 | 50
| Review | -5 | 51
Detail Schedule
Liên kết

## Detail Schedule
# | Item | Responsibilities | Start Date | End Date
1 | Create test plan | TranMinhTuong | 2024-11-01 | 2024-11-01
2 | Create test design | TranMinhTuong | 2024-11-01 | 2024-12-20
2.1 | Display Product Information | TranMinhTuong | 2024-11-01 | 2024-11-02
2.2 | Enter Customer Information | TranMinhTuong | 2024-11-07 | 2024-11-08
2.3 | Home Delivery | TranMinhTuong | 2024-11-17 | 2024-11-18
2.4 | Store Pickup | TranMinhTuong | 2024-11-23 | 2024-11-24
2.5 | Apply Discount Code | TranMinhTuong | 2024-11-29 | 2024-11-30
2.6 | Use Loyalty Points | TranMinhTuong | 2024-12-03 | 2024-12-04
2.7 | Company Invoice | TranMinhTuong | 2024-12-07 | 2024-08-12
2.8 | Personal Invoice | TranMinhTuong | 2024-09-12 | 2024-12-10
2.9 | Credit/Debit Card Payment | TranMinhTuong | 2024-12-11 | 2024-12-12
2.1.0 | Digital Wallet | TranMinhTuong | 2024-12-13 | 2024-12-14
2.11 | Bank Transfer | TranMinhTuong | 2024-12-15 | 2024-12-16
2.12 | Cash on Delivery | TranMinhTuong | 2024-12-17 | 2024-12-18
2.13 | Order Confirmation | TranMinhTuong | 2024-12-19 | 2024-12-20
3 | Create test case | TranMinhTuong | 2024-11-01
4 | Execute test and logs bug | TranMinhTuong | 2024-11-01
5 | Evaluting exit criteria & Test report | TranMinhTuong | 2024-11-01
6 | Review | TranMinhTuong

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1 | Test Plan | A document describing the scope, approach, resources, and schedule of testing activities.
2 | Test Design | The process of defining test cases and scenarios to validate system functionality.
3 | Test Case | A set of conditions or variables used to determine if the system behaves as expected.
4 | Test Execution | The process of running test cases and logging results.
5 | Bug Log | A record of all bugs identified during testing, including details and severity.
6 | Regression Testing | Testing to ensure new code changes don't adversely affect existing functionality.
7 | User Acceptance Testing | The process of verifying that the system meets business requirements and is ready for use.
8 | White Box Testing | Testing based on internal structures and code paths.
9 | Black Box Testing | Testing that examines system functionality without knowledge of internal code.
10 | Load Testing | Testing the system's performance under expected load conditions.
11 | Stress Testing | Testing the system's robustness under extreme load conditions.
12 | Test Environment | The setup including hardware, software, and network for testing activities.
13 | Test Coverage | A measure of how much testing has been done on the application.
14 | Exit Criteria | The conditions that must be met before testing can be concluded.
15 | Test Data | Data used during testing to validate system functionality.
16 | Defect Density | The number of confirmed defects per lines of code.
17 | Severity | The impact level of a defect on the system's operation.
Glossary
#
1 | SRS | Software Requirements Specification
2 | UAT | User Acceptance Testing
3 | QA | Quality Assurance
4 | API | Application Programming Interface
5 | UI | User Interface
6 | UX | User Experience
7 | LOC | Lines of Code
8 | CI/CD | Continuous Integration / Continuous Deployment
9 | TDD | Test-Driven Development
10 | BDD | Behavior-Driven Development
11 | ROI | Return on Investment
12 | POC | Proof of Concept
13 | KPI | Key Performance Indicator
14 | SLA | Service Level Agreement
Members
1 | TranMinhTuong