## Cover
TEST PLAN
Project Name | FPT Shop |  |  | Reviewer | Đặng Công Thuận
Project Code | FPT Shop |  |  | Review date | 2024-10-30
Creator | Đặng Công Thuận |  |  | Approver
Version | v1.0 |  |  | Approval Date | 2024-10-31
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
2024-10-30 | v1.0 | Initial | A
Index
Sheet Name | Description |  |  |  | Note
Cover | Title page
Test Policy | - General policy for Test process, Test case design, Test Data - List of requirements to Test/not Test - Exit criteria for testing - Suspension criteria and Resumption requirements
Test Management | - Test scope - Deliverable - Management method - Risk - Assumption - Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Appendix | - Description and detailed definition of Test level, types and techniques - List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
Note on E10: ====== ID#AAAAHNbKGmo (2020-11-08 05:44:12) - A: Added - D: Deleted - M: Modified

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
| # | Description | Responsibility | Note
| 1 | This policy ensures that every project has a clear test plan, including scope, resources, schedule, and acceptance criteria for test completion | Đặng Công Thuận | Ensure that all test planning documents are approved before commencing formal testing activities. The test plan should be updated as significant changes to requirements or resources occur.
| 2 | This policy defines how test execution and result recording are conducted, ensuring that all test cases are executed following the standard process and outputs are documented for later analysis | Đặng Công Thuận | All test results, including detected issues, must be fully recorded. Issue reports should include detailed information on the test environment and steps to reproduce the problem
Test case design policy
Description of policies of test case design.
| # | Items | Note
| 1 | Ensure that test cases are designed to fully cover functional requirements, including normal, exception, and boundary scenarios | All requirements must have at least one test case designed to verify their functionality. Test cases should be reviewed and approved to ensure no requirements are overlooked
| 2 | Test cases should be designed for reusability and maintainability, especially for future versions and releases | Avoid overly specific or data-dependent test cases. Test cases should be easy to adjust when requirements change, without needing to be entirely recreated
Quality metric
Description of target
| # | Items | Target | Note
|  | Defect Density: Number of defects found per unit size of software | ≤ 1 defect per 1000 lines of code | Ensuring low defect density is key to maintaining high software quality; often used in high-complexity projects.
|  | Test Coverage: Percentage of code covered by test cases. | ≥ 80% of total code | High coverage increases the likelihood of finding latent issues, especially in critical software functions.
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
| # | Criteria | Priority | Note
| 1 | 80% of completed test cases / total test cases (test coverage > 80%) |  | Carry out test cases with highest priority first, then increase gradually.
| 2 | Test successful coverage >= 80%
| 3 | Software is correct with SRS
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
| # | Suspension Criteria | Note
| 1 | When a defect is introduced that cannot allow any further testing
| 2 | A specific holiday shuts down both development and testing (Tet Holiday)
| 3 | If there is any network, hardware problem in the organisation, we can suspend testing
| 4 | If we got more pending requests with the development team
| # | Resumption Requirements | Note
| 1 | When the particular issue has been addressed and solved

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Create test plan | Define testing scope, objectives, resources, and schedule. |  | Leader / Testers
2 | Create test design | Outline testing approach and identify test scenarios |  | Tester
3 | Create test cases | Develop specific steps and expected outcomes for each scenario. |  | Tester
4 | Create test data | Prepare data sets required to execute test cases. |  | Teseter
5 | Execute system test | Run test cases to verify system functionality |  | Teseter
6 | Defects list | Document all identified defects with details for analysis |  | Teseter
7 | Create test report | Summarize test results, including defect findings and coverage status. |  | Leader / Testers
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 2024-10-31 | Test leader | Test manager, Team | This document itself
2 | Test cases | 2024-10-31 | Test leader | Test manager, Team
3 | Defect logs | 2024-10-31 | Test leader | Test manager, Team
4 | Test report | 2024-10-31 | Test leader | Test manager, Team
Management method
Describe the management method of test process.
# | Object | Method |  |  | Note
1 | Risk Management: Identifying and mitigating potential project risks. | Use risk assessment tools to evaluate and prioritize risks, then develop mitigation plans |  |  | Regularly update the risk register and monitor risks throughout the project lifecycle.
2 | Resource Management: Efficient allocation and utilization of resources (human, financial, material) | Use resource planning software and scheduling techniques. |  |  | Ensure resources align with project timelines and adjust as necessary to meet objectives
3 | Quality Management: Ensuring the project's deliverables meet defined quality standards. | Implement quality assurance (QA) and quality control (QC) processes. |  |  | Regular audits and reviews help maintain consistent quality across project phases.
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  | Mitigation |  | Contingency
1 | Team members lack experience in software testing domain |  | Plan training course to skill up your members |  | 1. Connect with a training organization 2. Attend mandatory training 3. Quality test
2 | The development team improved the code which led to the testing process being paused |  | Accept this risk |  | Contact the development team
3 | The project schedule is too tight; it's hard to complete this project on time |  | Set test priority for each test case and execute the test case with the highest priority |  | 1. Determine the priority for each test case 2. Set priority for each test case 3. Follow the priority level
4 | Members misunderstood the request |  | Organize to review and analyze requirements to member before starting the testing process |  | 1. Hold a meeting 2. Review required 3. Inspections
5 | Employees reduce working performance after Tet holiday |  | Accept this risk |  | OT to keep up with the schedule
Assumption
Listing of all assumption of test process.
# | Type | Description
1 | Stable Requirements: Project Assumption | It is assumed that the project requirements are stable and will not undergo major changes during the testing phase to ensure test cases remain relevant and accurate.
2 | Availability of Test Environment: Resource Assumption | A fully configured test environment, closely resembling the production environment, will be available before the test execution phase begins to ensure reliable and consistent testing outcomes
Training Plan
Plan training for test team.
# | Training Topic | Description |  | Responsibility | Start Date | End Date
1
2
3
Note on E32: ====== ID#AAAAHNbKGmc (2020-11-08 05:44:12) steps keep a risk from occurring or driving its impact to an acceptance level
Note on G32: ====== ID#AAAAHNbKGmk (2020-11-08 05:44:12) steps would have to be done if the risk were to become reality
Note on B41: ====== ID#AAAAHNbKGmY It can be (2020-11-08 05:44:12) - Requirement - Test Products - Test environment - Test tools ...

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x |  | x
Black box testing |  | x | x | x
Responsibility | Developer | Tester | Tester | Tester
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
All Functions of the FPTShop system described in screen design document, the functions are tested in order of priority from high to low (highest priority tested first)
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop, Tablet, Smartphone |  |  |  | Standard Fsoft
OS | Window 10 64bit Mac10.14.5 Android 6.0 or higher
Software | Chrome version 78.0.3904.97 Firefox 70.0 Edge 44.18362.329.0
Database | MS SQL
Browser | IE/FireFox, Chrome
Network configured | LAN Wifi
Note on G10: ====== ID#AAAAHNbKGmg (2020-11-08 05:44:12) - manual - test tool …

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
1 | Đặng Công Thuận | Leader | Read and analyze documents, create test design, create test cases, execute test cases, log bugs, evaluate exit criteria, and compile the test report for Shopping Cart function
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan | 2024-10-30 | 2024-10-31
2 | Create test design | 2024-11-01 | 2024-11-04
3 | Create test case | 2024-11-05 | 2024-11-07
4 | Execute test and log bugs | 2024-11-08 | 2024-11-11
5 | Evaluting exit criteria & Test report | 2024-11-12 | 2024-11-15
6 | Review | 2024-11-16 | 2024-11-20
| Task | Start day from 9/12/2019 | Duration
| Create test plan | 0 | 1
| Create test design | 1 | 3
| Create test case | 4 | 2
| Execute test and log bugs | 6 | 3
| Evaluting exit criteria & Test report | 9 | 3
| Review | 12 | 5
Detail Schedule
Liên kết

## Detail Schedule
# | Item | Responsibilities | October |  | November
|  |  | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Create test plan | Đặng Công Thuận | bar: October 30 to October 31
2 | Create test design | Đặng Công Thuận
2019-01-02 | Add Item to Cart | Đặng Công Thuận
2019-02-02 | Update Item Quantity | Đặng Công Thuận
2019-03-02 | Remove Item from Cart | Đặng Công Thuận
2019-04-02 | View Cart Summary | Đặng Công Thuận
2019-05-02 | Apply Discount Code | Đặng Công Thuận
2019-06-02 | Proceed to Checkout | Đặng Công Thuận
2019-07-02 | Save Cart for Later | Đặng Công Thuận
2019-08-02 | Cart Persistence Across Devices | Đặng Công Thuận
3 | Create test case | Đặng Công Thuận | bar: November 5 to November 7
4 | Execute test and logs bug | Đặng Công Thuận | bar: November 8 to November 11
5 | Evaluting exit criteria & Test report | Đặng Công Thuận | bar: November 12 to November 15
6 | Review | Đặng Công Thuận | bar: November 16 to November 20

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
17
Glossary
#
1
1
2
3
4
#
4
5
6
7
8
9
10
11
12
13
14
Members
1 | Đặng Công Thuận